## 翰陞Weekly Report
Weekly Report
Team Member: 翰陞
Date:2024
Task Status in current week
Project | Task
| Task name | Status | Complete Rate | Start Date | End Date | # of bug found | Block% | Note (Delay reason, issue, help)
MWPPG | 完成表一表二 | On-going |  | 2024-12-20 | 2024-12-27
MWPPG | 擴充資料集
Task Planning in coming week
Project | Task
| Task name | Status | Complete Rate | Start Date | End Date | # of bug found | Block% | Note (Delay reason, issue, help)

## 芮綺Weekly Report
Weekly Report
Team Member: 芮綺
Date:2024
Task Status in current week
Project | Task
| Task name | Status | Complete Rate | Start Date | End Date | # of bug found | Block% | Note (Delay reason, issue, help)
MWPPG | 完成表三 | On-going |  | 2024-12-20 | 2024-12-27
MWPPG | 嘗試量測出自己的PPG訊號 | Completed | 100% | 2024-12-20 | 2024-12-27
MWPPG | 驗證新殼量測效果 | On-going |  | 2025-01-03
MWPPG | 擴充資料集
Task Planning in coming week
Project | Task
| Task name | Status | Complete Rate | Start Date | End Date | # of bug found | Block% | Note (Delay reason, issue, help)

## 凱鋒Weekly Report
Weekly Report
Team Member: 凱鋒
Date:2024
Task Status in current week
Project | Task
| Task name | Status | Complete Rate | Start Date | End Date | # of bug found | Block% | Note (Delay reason, issue, help)
MWPPG | 3D列印新殼 | On-going | 50% | 2024-12-20 | 2024-12-31
MWPPG | 嘗試在裝置上顯示PPG訊號 | Completed | 100% | 2024-12-17 | 2024-12-20
MWPPG | 多版本曝光模式 | Completed | 100% | 2024-12-20 | 2024-12-31
MWPPG | 改變取樣頻率試試看效果 | Completed | 100% | 2024-12-20 | 2024-12-31
Task Planning in coming week
Project | Task
| Task name | Status | Complete Rate | Start Date | End Date | # of bug found | Block% | Note (Delay reason, issue, help)